## Sheet1
id | Title | Desc | raised date | Category | Sev | Pri | status | Owner | closed on | Comment
1 | Hop Count Revision | count overlapping jobs and the immediate next job. Currently finding less counts than what we theoretically expected. | 2024-04-16 | bug | M | H |  | Erin
2 | Data Processing Revision | Currently excluding profiles with non-US and unclassified jobs. Want to them back, but incurring a memory error. | 2024-04-11 | bug | M | H | Closed | Eugene | 2024-04-23
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20